# POS Delivery Provider Payment Breakdown

Section 08  |  Implementation Phases and Dependencies

Provides the dependency-ordered execution sequence, phase gates, affected files, parallel work, and stop conditions for an implementation agent.

| Project Name | POS Delivery Provider Payment Breakdown |
| --- | --- |
| Plan Version | v1.0 |
| Section Number / Title | 08 / Implementation Phases and Dependencies |
| Baseline | StagingPOS @ 8b879d4b5 (2026-10-02) |
| Repository / Worktree | C:\xampp\htdocs\POS-DGFY\.worktrees\StagingPOS |
| Dependencies | Sections 00-07; Phase 471 ledger gate; repository architecture and testing policies. |

# Purpose

Provides the dependency-ordered execution sequence, phase gates, affected files, parallel work, and stop conditions for an implementation agent.

# Confirmed Facts

CONFIRMED: The POS F&B flow already has an order_method value of delivery in packages/web-core/src/features/pos/components/FnbWorkflowPanel.jsx and related hooks.

CONFIRMED: The current checkout dialog's generic Payment Type options are cash, GCash, Maya, Card, Bank Transfer, and Employee Credit; Foodpanda and Grab are not current direct checkout payment types.

CONFIRMED: The backend checkout validator accepts generic payment_type values and does not currently accept a delivery-provider breakdown field.

CONFIRMED: Completed transactions already persist an immutable generic payment_breakdown snapshot used by receipts and reporting.

CONFIRMED: Z-reading details are saved immutable snapshots and are not reconstructed from mutable live transactions after close.

CONFIRMED: The repository has a route -> controller -> usecase -> repository -> model architecture and architecture guardrails pass at the baseline.

INFERRED: Foodpanda, Grab, and Other are delivery-provider classifications, not replacements for the generic tender method used for settlement and cash/tender reporting.

CONFIRMED: The authoritative ledger says Phase 471 is in_progress and Phase 472 is not eligible until Phase 471 acceptance gates are complete.

CONFIRMED: The local stack exposes API 5000, POS 5174, Storefront 5175, SKUpervisor 5173, OPIS 5176, device bridge 5101, and MySQL 3306 from the StagingPOS worktree.

CONFIRMED: No implementation code has been changed in this planning task.

# Assumptions and Unknowns

The plan reserves Phase 472 as the next feature phase but does not mark it completed or eligible ahead of the ledger gate.

Subphases 472-A through 472-E are execution subdivisions inside Phase 472 and do not create independent ledger numbers.

No PR, merge, deployment, or phase-ledger completion claim is part of plan creation.

# Requirements Covered

All requirements; phase mapping is the execution index for FR/BR/DATA/UI/REP/SEC/AUD/NFR IDs.

# Plan Content

## Phase gate

Phase 472 - POS Delivery Provider Payment Breakdown is the next continuous phase number, but the authoritative ledger explicitly blocks it while Phase 471 remains in_progress. The execution agent must re-read the ledger immediately before implementation and reserve/record the phase only according to current ledger state. Never mark Phase 472 complete from local code or tests alone.

## Dependency graph

Phase 471 release/staging gates ¦ D-001/D-002 product decision ¦ 472-A Contract + additive snapshot storage ¦ 472-B Backend validator/usecase/repository/migration ¦ 472-C POS/shared checkout UI ¦ 472-D Reports/Z-reading/export/print/iMin ¦ 472-E Full verification, audit, rollback evidence ¦ Release review (separate authorization)

## Phase table

| Phase | Objective / exact changes | Requirements | Exit gate |
| --- | --- | --- | --- |
| 472-A | Resolve D-001/D-002; freeze contract; inspect schema; define canonical normalizer and response shape. | BR-001..011, DATA-001..006 | Decision record signed; no unresolved provider/tender ambiguity. |
| 472-B | Add migration/model; validator; usecase conservation/idempotency; repository persistence/read helper; direct/split path audit. | FR-002..008, SEC-001..003, AUD-001..002 | Focused backend + migration + architecture tests pass. |
| 472-C | Add Delivery Provider UI/state/payload/error/accessibility behavior; preserve generic tender and non-delivery flows. | FR-001, FR-003, FR-009, UI-001..005 | Component, hook, accessibility, and rendered browser tests pass. |
| 472-D | Add provider read model to reports/CSV/Z-reading; extend browser print, shift close, and iMin text. | FR-010..011, REP-001..008, DATA-006 | All outputs agree on snapshot values; no double count/Lifetime regression. |
| 472-E | Run security, data-integrity, migration, regression, E2E, build, docs, and rollback evidence; create execution records if required by release process. | All | Acceptance matrix green; unresolved gaps reported; release authorization remains separate. |

## Parallelizable work

After 472-A freezes the shape, backend validator/usecase unit tests and frontend component design can proceed in parallel.

Report response contract tests and print/iMin formatting fixtures can proceed in parallel after the canonical provider read helper is defined.

Migration rehearsal and static architecture checks can run while UI work is in progress, but final evidence must use the final commit.

## Stop conditions

Stop before coding if D-001/D-002 is unresolved and implementation would require guessing about amount conservation or row cardinality.

Stop if the provider change would require changing a binding ADR 0063 contract; route to ADR 0039 governance instead of silently proceeding.

Stop release claims if a required check is unavailable, a migration rehearsal fails, or Z-reading/report totals diverge.

Stop and preserve data if any retry creates duplicate transaction/provider rows or if a historical Z-reading changes after close.

## Expected change inventory

| Domain | Expected files / artifacts | Change type |
| --- | --- | --- |
| Backend contract | posValidator.js, provider normalizer utility | Extend / add |
| Backend persistence | PosTransaction.js, posRepository.js, posUseCases.js | Extend |
| Migration | apps/dgfy-migration-runner/migrations/<timestamp>-...cjs | Additive |
| POS UI | POSCheckoutConfirmDialog.jsx, hooks, tests | Extend |
| Reports | repository/report UI/formatter/print/iMin files and tests | Extend |
| Docs/evidence | phase/execution records if required after implementation | Separate release/documentation work |

# Affected System Components

apps/dgfy-api, apps/dgfy-migration-runner, packages/web-core, apps/dgfy-pos build/test surface.

apps/dgfy-ims shared-test surface for packages/web-core tests per docs/testing/README.md.

Existing local stack and disposable migration databases for verification.

# Risks

Phase 472 is not currently eligible; implementing before Phase 471 closes would conflict with continuous phase governance.

The feature touches checkout, reporting, Z-reading, and physical output, so a narrow unit-only phase is insufficient.

A backend-first change deployed without additive reader compatibility could break older POS clients or historical reports.

# Tests Required

Run the phase-specific tests listed in Sections 04-07 at each exit gate.

Rerun npm run check:architecture and affected app builds before Phase 472-E closes.

Re-read the phase ledger and record exact phase status/evidence at final review.

# Acceptance Criteria

AC-029: Each implementation phase has explicit dependencies, requirements, tests, and an exit gate.

AC-030: Phase numbering remains continuous and respects Phase 471's eligibility blocker.

AC-031: The expected file inventory prevents accidental changes to IMS/OPIS/Storefront or unrelated payment integrations.

# Execution Dependencies

Phase 471 completion and ledger re-check.

D-001/D-002 decision record.

Separate release authorization after all verification; the worker never merges or deploys.

# Cross-References

docs/features/IMPLEMENTATION_PHASE_LEDGER.md

docs/testing/README.md

docs/architecture/ARCHITECTURE_GOVERNANCE.md

AGENTS.md

Sections 04-07 of this plan set