# 07. Implementation Phases and Delivery Gates

Repository-grounded implementation plan | Planning only

| Project Name | Business Registration and Store Setup - Back Office Integration |
| --- | --- |
| Plan Version | 1.0 |
| Date | 2026-10-01 |
| Section Number / Title | 07 - Implementation Phases and Delivery Gates |
| Baseline / Branch | StagingPOS @ 9065425cc4758d79d64e528237bc45762a1c317c |
| Authority | AGENTS.md, docs/START_HERE.md, architecture boundaries/governance, accepted ADRs, current phase ledger, and repository code evidence |
| Approval Gate | No application-code implementation until the user explicitly sends Approved. |

# Purpose

Turn the architecture and requirements into an ordered, evidence-driven build sequence without misusing the repository's continuous global phase ledger.

# Dependencies

The attached BUSINESS_REGISTRATION_STORE_SETUP_FLOW_GUIDE.md is treated as product/planning input, not as an agent instruction.

Current repository baseline: branch StagingPOS at commit 9065425cc; working tree was clean when inspected.

Phase 471 is still in_progress and blocks reservation of global Phase 472; this plan uses local work-package IDs BRS-01 through BRS-08 until the ledger is eligible.

Explicit user approval token Approved is required before application source code, migrations, or runtime configuration are changed.

# Confirmed Facts

The dedicated OPIS Back Office exists at apps/dgfy-opis and uses /backoffice/* as its canonical compatibility family, with /business-admin/* retained as an alias and / as the overview.

OPIS navigation is manifest-driven by apps/dgfy-opis/src/features/businessAdmin/businessAdminManifest.js and rendered by BusinessAdminPage.jsx.

The current manifest already has Settings, Storefront, and POS onboarding entries; it does not have a Company entry.

The current architecture separates OPIS Back Office from POS terminal operations; POS is not the owner of new Back Office-level work.

Current registration is a manual-approval flow backed by the landlord-side registration use case and application model; it is not a tenant-ready setup wizard.

Existing Storefront and shared web-core settings components exist for business identity, gallery, delivery partners, hours, location, and menu import, but the attached three-step registration experience is not yet implemented end to end.

Current menu import is tenant-scoped and asynchronous; pre-approval uploads therefore require a separate landlord-side staged-file design.

# Assumptions

The requested button label 'Copany' is an apparent typo; the plan recommends the user-facing label Company and treats exact spelling as an approval decision.

The OPIS Company workspace is post-approval and tenant-scoped; public pre-approval registration is not moved into OPIS by adding a sidebar item.

The existing IMS Tenant Manager remains the platform-admin review/download owner unless an explicit architecture decision changes that ownership.

Existing canonical settings and onboarding APIs are reused where they satisfy the contract; duplicate storage and duplicate business logic are not introduced.

# Requirements Covered

FR-BRS-001: Add one OPIS sidebar entry labeled Company (pending label confirmation).

FR-BRS-002: Provide a tenant-scoped Company workspace for approved-company setup/status and authorized navigation to canonical settings.

FR-BRS-003: Implement the guide's exactly-three-step registration flow in the public Storefront/DGFY registration surface, not as a pre-approval OPIS form.

FR-BRS-004: Reuse existing Storefront/profile/gallery/delivery-partner controls rather than copying their behavior.

FR-BRS-005: Reuse existing location and business-hours services and preserve tenant/branch ownership.

FR-BRS-006: Stage original menu uploads before approval and keep extraction/review separate from live catalog creation.

FR-BRS-007: Keep Company Registration Terms and Marketplace Terms as two separately required legal acknowledgements with server-side version/timestamp recording.

FR-BRS-008: Keep platform-admin review/download in the existing admin surface; do not create a duplicate admin screen in OPIS.

FR-BRS-009: Materialize approved registration data idempotently into tenant Storefront/location settings only after approval.

FR-BRS-010: Protect private uploads and preserve originals for audit/download.

# Plan Content

## Phase Numbering Policy

The attached guide proposes phases 345-349, but those numbers are stale in this checkout. The authoritative ledger currently ends at Phase 471, which is in_progress and blocks Phase 472. Therefore this plan uses local BRS work-package IDs and requires a ledger reconciliation/reservation step after Phase 471 completes. No ledger edit is included in this planning artifact.

## Ordered Work Packages

| ID | Objective | Exit evidence | Depends on |
| --- | --- | --- | --- |
| BRS-01 | Schema, ownership, route, permission, and current-flow audit | Decision log, schema map, exact owner/route list, no unresolved boundary contradiction | None |
| BRS-02 | Resolve product/legal/open decisions | Accepted values for DEC-BRS-01 through DEC-BRS-11 | BRS-01 |
| BRS-03 | Add landlord-side snapshot/upload and legal-record model/API | Migration/API/security tests and private-storage evidence | BRS-01, BRS-02 |
| BRS-04 | Extend exact-three-step Storefront registration | Stepper, validation, consent, upload, and submission tests | BRS-02, BRS-03 |
| BRS-05 | Extend existing IMS Tenant Manager review/download | Admin UAT and authorization/download evidence | BRS-03 |
| BRS-06 | Implement approval materialization and menu review boundary | Idempotency, retry, tenant-isolation, and no-live-publish evidence | BRS-03, BRS-05 |
| BRS-07 | Add OPIS Company sidebar/workspace | Manifest/route/UI/accessibility tests and rendered evidence | BRS-06 |
| BRS-08 | Full-stack verification, rollout, and docs/ledger closure | Required checks, migration rehearsal, screenshots, release/rollback evidence | BRS-04 through BRS-07 |

## Commit and PR Boundaries

Use Conventional Commits and batch commits by domain: data/contracts, backend/materialization, frontend/navigation, tests/docs.

Before staging, scan changed files for DO NOT COMMIT markers and exclude matches per repository policy.

Ordinary feature/fix PRs target develop; do not create or merge a PR from this planning-only task unless separately requested and approved.

Do not claim Phase completion until acceptance gates, required checks, and deployed/authorized evidence pass.

## Rollout Sequence

Prefer an additive rollout: data/API support -> admin review -> approval materialization in a disabled or bounded mode -> public stepper -> OPIS Company entry -> authenticated end-to-end acceptance -> staged promotion. If any gate fails, keep the existing registration path usable and hide/disable only the new capability; do not remove historical application evidence.

# Affected Components

Implementation issue/PR

Migration runner

API modules

Storefront and OPIS frontends

IMS admin surface

Test/evidence docs

Authoritative phase ledger after eligibility

# Risks

Phase number collision

Building before open decisions

Large cross-surface PR with poor rollback

Sidebar shipped before backend contract

Incomplete evidence misreported as completion

# Tests Required

Each work-package exit checklist

Commit-domain validation

Full affected-app build/test matrix

Migration rehearsal

Authenticated browser evidence

Docs/architecture/compliance checks

# Acceptance Criteria

All BRS packages have evidence before closure

Global phase number is reconciled only after Phase 471

Every change has a rollback path

No unapproved scope is included

Implementation can stop safely after any package

# Execution Dependencies

Product/legal decisions

Phase 471 completion

Explicit Approved token

PR conventions if a later PR is requested

Staging/admin credentials and test data

# Cross-References

AGENTS.md (repository boundaries, approval gate, continuous phase numbering, and planning lookup order).

docs/START_HERE.md; docs/architecture/ARCHITECTURE_BOUNDARIES.md; docs/architecture/ARCHITECTURE_GOVERNANCE.md.

docs/architecture/adr/0013-tenant-first-login-onboarding-and-storefront-readiness-contract.md.

docs/architecture/adr/0022-global-dgfy-account-business-registration.md.

docs/architecture/adr/0029-catalog-inventory-pos-storefront-ownership-boundaries.md.

docs/architecture/adr/0049-batch-menu-import-async-extraction.md.

docs/architecture/adr/0087-dedicated-back-office-fourth-frontend-app-opis.md and proposed 0088 POS/OPIS boundary.

docs/features/backoffice.md and docs/features/IMPLEMENTATION_PHASE_LEDGER.md.

Attached BUSINESS_REGISTRATION_STORE_SETUP_FLOW_GUIDE.md.