# Implementation Rollout Rollback and Risks

Section 06 | Ordered delivery, release gates, monitoring, recovery and phase sequencing

| Field | Value |
| --- | --- |
| Project Name | DGFY POS Reports Analytics Expansion |
| Plan Version | 1.0 |
| Section Number | 06 |
| Section Title | Implementation Rollout Rollback and Risks |
| Purpose | Turn the approved plan into a controlled implementation and release sequence with explicit stop conditions. |
| Dependencies | Sections 01-05; phase ledger; release/PR policy; architecture governance and testing evidence. |

# Plan Content

Implementation should proceed in small, reviewable batches. The sequence below keeps the backend contract ahead of the UI, proves invariants before staging, and preserves a straightforward rollback because the selected design is additive and read-only.

# Local Implementation Phases

| Phase | Exact work | Exit criteria |
| --- | --- | --- |
| RPT-01 Contract freeze | Close open decisions, finalize IDs and response examples, confirm maximum range/pagination/category policy, reconcile phase ownership. | Requirements signed off; contract fixtures ready; no unresolved binding architecture conflict. |
| RPT-02 Backend | Implement validator/route/controller/usecase/repository breakdown path, export sections, tests and structured telemetry. Reuse normalized lines and scope helpers. | Backend tests, API contract tests, architecture check and static checks pass. |
| RPT-03 Frontend | Implement tabs, breakdown fetch state, tables, filters, pagination/sort, print/export, offline snapshot envelope and component tests. | Focused shared tests and affected builds pass; existing tabs regressions are green. |
| RPT-04 Integrated verification | Run reconciliation, authorization matrix, malformed-query tests, performance measurements, CSV fidelity and browser checks. | Critical verification matrix rows pass and evidence is tied to candidate SHA. |
| RPT-05 Staging UAT | Seed isolated staging data; execute desktop/mobile report journeys; collect screenshots, CSVs, console/network logs and performance artifact. | Product acceptance and QA evidence complete; no open critical defect. |
| RPT-06 Rollout/closeout | Release through normal branch policy, monitor metrics, verify rollback readiness, record final evidence and update implementation/phase records after actual completion. | Release gates pass; monitoring window is clean; closeout record links code and evidence. |

# Release and Rollout Plan

Keep the change additive: existing overview, current tabs, permissions and export sections must work even if the new breakdown UI is disabled or rolled back.

Run all required checks on the candidate commit before staging. Do not treat a local green result as staging proof.

Deploy to staging first, execute the full UAT/evidence matrix, and inspect endpoint duration, query count, payload size, export failures and authorization denials.

Promote only through the repository’s current PR/release policy after the candidate SHA and evidence are reconciled. This plan does not authorize a merge, push or deployment.

During the observation window, compare breakdown totals with the existing overview for representative ranges and scopes.

# Monitoring and Stop Conditions

| Signal | Action threshold / response |
| --- | --- |
| 5xx or query failures | Stop rollout and investigate; no partial UI success is accepted. |
| Authorization failures | Check scope regression and tenant/branch fixtures; stop if failures are unexpected or any data leaks. |
| Slow p95 or high query count | Compare to baseline; disable new view or roll back if agreed budget is exceeded. |
| Large payload/export timeout | Reduce allowed range/limit or roll back before increasing infrastructure load. |
| Summary mismatch | Stop immediately; reconcile normalized line and distinct-order logic before further rollout. |
| Empty scope unexpectedly | Check location/cashier resolution and data seed; never broaden scope as a workaround. |

# Rollback Plan

Application rollback: revert the UI and endpoint commits or disable new report tabs through the normal release mechanism. Existing overview/export remain the fallback.

Data rollback: none expected because no persisted aggregate table or destructive migration is planned. If a performance index is later approved, its rollback must be a separately tested migration step.

Evidence rollback: retain failed candidate logs and screenshots; record the exact reverted SHA and reason. Do not delete evidence needed to explain a release decision.

After rollback, re-run existing overview, sales, export, authorization and no-mutation smoke tests to prove the baseline is intact.

# Phase Numbering and Documentation Warning

The authoritative ledger docs/features/IMPLEMENTATION_PHASE_LEDGER.md currently ends at Phase 347, which remains in_progress, and says Phase 348 is eligible only after Phase 347 implementation, review, merge and deployed QA gates. A separate Implementation.md section names phases 348-350 for a device/location sequence but is not the authoritative ledger. This plan intentionally uses initiative-local RPT-01 through RPT-06 IDs. Before implementation starts, the owner/PM must reconcile the ledger and reserve the next valid global phase number; this plan does not overwrite or pre-claim Phase 348.

# Plan Consistency Audit

| Check | Result |
| --- | --- |
| Requirement coverage | FR, BR, DATA, SEC, PERM, UI, REP, NFR, MIG and OPS IDs are mapped across backend, frontend and verification sections. |
| Architecture boundary | Selected path remains routes -> controller -> usecase -> repository; reports remain read-side POS work. |
| Financial source of truth | Existing normalized line pipeline is reused; no parallel calculation source is introduced. |
| Historical data | No rewrite or migration; snapshot item identity and live category semantics are explicit. |
| Security | Tenant/location/cashier scope and allowlist validation are tested before UI acceptance. |
| Rollback | Additive code and no migration provide a reversible release; any future index is separately gated. |
| Documentation freshness | Required authoritative and domain docs were read; final implementation must re-check freshness at execution time. |
| Phase continuity | Global number is intentionally unresolved until Phase 347/348 ledger conflict is reconciled. |

# Confirmed Facts

The feature can be delivered as an additive read-only capability.

Existing release and PR controls remain authoritative for any later implementation.

The rollback path does not require deleting user data.

# Assumptions

Staging can support an isolated, representative report dataset.

A normal application revert is sufficient if no performance migration is added.

# Requirements Covered

OPS-REP-001

OPS-REP-002

OPS-REP-003

NFR-REP-001 to 004

All master acceptance criteria

# Affected Components

apps/dgfy-api and packages/web-core implementation batches

staging environment and evidence storage

phase ledger and release records

# Risks

Rollout continues despite summary mismatch or scope leakage.

Phase numbering is assigned without reconciling the authoritative ledger.

A future index migration is bundled without measured query evidence.

# Tests Required

Candidate gate logs

Staging UAT evidence

Monitoring snapshot

Rollback smoke test

Final plan/ledger update

# Acceptance Criteria

Release is additive and observable.

Rollback restores the prior report behavior.

Phase status is not marked completed until acceptance evidence exists.

# Execution Dependencies

RPT-06 is eligible only after RPT-04 and RPT-05.

No code, commit, PR, issue or deployment is created by this plan.

A future implementer must preserve the dirty-worktree safety rule.

# Cross-References

docs/features/IMPLEMENTATION_PHASE_LEDGER.md

docs/ai/PR.md

docs/architecture/ARCHITECTURE_GOVERNANCE.md

docs/ops/RELEASE_CANDIDATE_POLICY.md

docs/testing/README.md