# Implementation Phases and Dependencies

POS BIR Annex B Items 4 to 14 Readiness | Plan version 1.0 | Section 08

| Project name | POS BIR Annex B Items 4 to 14 Readiness |
| --- | --- |
| Plan version | 1.0 |
| Repository baseline | C:\xampp\htdocs\POS-DGFY ¦ branch feat/DGFY-343-2067-pos-workflow-consolidation ¦ HEAD 786cd4e8329db1a65398ce6aa7eb020ffc8f3b28 |
| Planning mode | Planning only. This artifact does not implement code, migrations, configuration, or release actions. |

# Purpose

Convert the design into a continuous, dependency-aware implementation sequence starting after the current repository ledger maximum of Phase 352.

# Dependencies

Sections 00-07.

Current phase ledger re-check before implementation.

Local-only execution constraint.

# Confirmed Facts

The phase ledger highest observed phase is 352 and is marked in_progress.

The plan therefore proposes Phase 353 onward without modifying Phase 352.

The sequence is intentionally additive and reversible; phases cannot be marked completed until their acceptance and validation evidence passes.

Some phases are documentary/operational, not code-only. They still require owners, tests, and evidence.

# Assumptions and Unknowns

The phase ledger remains at 352 when implementation starts; if another phase is added first, renumbering is not allowed and this plan must be reconciled.

Implementation branches will be clean or path-scoped; unrelated dirty root changes remain untouched.

Each phase may be split into PR-sized commits, but the continuous phase number remains the same.

# Requirements Covered

| ID | Requirement |
| --- | --- |
| OPS-401 | Maintain continuous phase numbering and evidence-backed completion. |
| FR-401 to FR-410 | Implement Items 4 through 14 in dependency order. |
| MIG-401 | Run additive schema and tenant-clone validation before behavior gates. |
| TEST-480 | Each phase has tests and exit criteria. |
| AC-480 | Do not mark a phase completed on code existence alone. |

# Plan Content

## Proposed phase sequence

| Phase | Objective | Main output | Depends on | Exit gate |
| --- | --- | --- | --- | --- |
| 353 | Source lock and control matrix | Current BIR/tax/e-journal source decision, Annex matrix, fixture registry, ADR/compliance declaration. | Current ledger | Sources and owners locked; no invented grammar. |
| 354 | Fiscal receipt completeness | Item 4 scenario contracts, fixtures, renderer/evidence samples, reconciliation. | 353 | All applicable receipt fixtures pass. |
| 355 | Adjustment document lifecycle | Item 5 cancel/void/refund/return decision and immutable linked documents. | 353, 354 | Every applicable adjustment sample links original number. |
| 356 | X/Z readings and reconciliation | Item 6 payload/print/evidence outputs and source reconciliation. | 354, 355 | X/Z totals and snapshots reconcile. |
| 357 | Report catalog and samples | Item 7 report inventory, applicability, samples, checksums, reviewer view. | 354-356 | Catalog equals exposed report capability. |
| 358 | E-journal serializer and export | Item 8 versioned .txt, hard-copy projection, manifest, completeness gate. | 353-357 | One-to-one source mapping and hash parity. |
| 359 | System narrative, version, connectivity | Items 9-11 refreshed docs, screenshots, online/offline evidence. | 354-358 | Screenshots and narrative match exact build. |
| 360 | Manual, audit, DRP | Items 12-14 manual, audit print/export, DRP, restore/encryption proof. | 353-359 | Operator/manual and DR drill gates pass. |
| 361 | Security, migration, and readiness gate | RBAC, append-only, schema, retention, artifact freshness, computed score. | 353-360 | Security/migration/compliance gates pass. |
| 362 | Local release rehearsal and evidence freeze | Local build, tests, evidence packet, rollback rehearsal, internal sign-off. | 361 | All Items 4-14 internal pass or approved N/A; external pending listed. |

## Phase execution rules

Phase 353 is a hard stop for unresolved source/grammar/tax decisions. Later phases may build scaffolding, but final evidence cannot be frozen before it passes.

Phases 354 through 358 are the core fiscal/report/e-journal runtime work. They must share immutable source records and one reconciliation strategy.

Phases 359 and 360 produce documentary evidence only after the tested runtime behavior is stable; screenshots/manual/DRP generated earlier are drafts.

Phase 361 is the gate that prevents a green UI or PR from being called 100 percent when permissions, tenant scope, migration, immutability, or artifact freshness fail.

Phase 362 is local-only release rehearsal. It does not deploy staging or production, and it does not claim external BIR acceptance.

## Parallel work allowed

Phase 353 source review, control matrix drafting, and current evidence inventory may run in parallel, but the grammar and legal decisions must converge before serializer freeze.

The Item 9 narrative skeleton, Item 12 manual outline, and Item 14 DRP review can run in parallel with runtime work; their final versions depend on tested behavior.

Security/permission design and migration design may run in parallel with UI design; no UI action may be exposed before backend authorization contracts exist.

# Affected System Components

| Classification | Components and expected treatment |
| --- | --- |
| Phase ledger | docs/features/IMPLEMENTATION_PHASE_LEDGER.md; reserve 353 after reconciliation and record status/evidence links. |
| Implementation | apps/dgfy-api, apps/dgfy-migration-runner, apps/dgfy-pos, packages/web-core, packages/pos-receipt. |
| Evidence | docs/compliance, generated local evidence, final-review artifacts, test reports. |
| Release | Local stack, local MySQL/Redis where required, builds, rollback rehearsal; no staging dependency. |

# Risks and Mitigations

| ID | Risk | Mitigation |
| --- | --- | --- |
| R-080 | Phase 352 remains incomplete and phase numbering drifts. | Re-check ledger; preserve 352; reserve 353 only after sequence reconciliation. |
| R-081 | A later phase starts before grammar/source lock. | Keep Phase 353 exit gate mandatory for final completion. |
| R-082 | Document work is treated as optional. | Make each document/manual/drill an acceptance artifact and owner. |
| R-083 | Phase completion is asserted from PR status. | Require automated/manual evidence and phase ledger entry. |

# Tests Required

| Test ID | Type | Scenario and evidence |
| --- | --- | --- |
| TEST-480 | Ledger | Verify phase numbers, status vocabulary, dependency links, evidence paths, and completion date rules. |
| TEST-481 | Phase gates | Run each phase's targeted tests and record pass/fail/blocked evidence. |
| TEST-482 | Dependency | Attempt final readiness with each prerequisite missing and verify deterministic blocker. |
| TEST-483 | Local release | Run complete local gates and ensure no staging credentials or network dependency is required. |

# Acceptance Criteria

| ID | Measurable acceptance criterion |
| --- | --- |
| AC-480 | The implementation sequence starts at proposed Phase 353 and does not reset numbering or overwrite Phase 352. |
| AC-481 | Every phase has objective, output, dependency, risks, tests, and exit gate. |
| AC-482 | No phase is eligible for completed status without its evidence and acceptance gates. |
| AC-483 | The sequence ends in a local release/evidence freeze, not an unapproved deploy. |

# Execution Dependencies

Re-read the phase ledger immediately before creating the implementation branch.

Update the ledger through the governed PR when Phase 353 is actually started; do not modify it during this planning-only task.

Implement each phase with path-scoped commits and required compliance/architecture declarations.

Link each phase to tests, artifacts, and acceptance rows.

Use Phase 362 as the final local completion checkpoint.

# Cross References

docs/features/IMPLEMENTATION_PHASE_LEDGER.md.

docs/architecture/ARCHITECTURE_GOVERNANCE.md.

docs/compliance/rmo-24-2023-gap-closure-plan.md (reference only; correct its stale ADR/path references during implementation).

docs/compliance/compliance-ops-regulatory-verification.md.