# Configurable Payment Processing Fee

Implementation Phases and Dependencies

| Project name | POS-DGFY |
| --- | --- |
| Plan version | 1.0 |
| Section | 08 Implementation Phases and Dependencies |
| Purpose | Convert the design into an execution-ready Phase 474 sequence with dependencies, risks, tests, and exit criteria. |
| Dependencies | Current ledger: Phase 473 in progress and Phase 474 next eligible; Sections 02 through 07; ADR amendment approval. |
| Implementation status | Planning only. No application code is changed by this plan. |

# Continuous phase position

The authoritative ledger ends with Phase 473. Its next eligible phase is Phase 474, subject to Phase 473 acceptance gates and a ledger recheck. This plan reserves Phase 474 for the configurable payment processing fee capability and does not renumber or mark any existing phase.

# Phase 474 workstreams

| Workstream | Objective and exact changes | Dependencies | Exit criteria |
| --- | --- | --- | --- |
| 474.0 Decision and governance | Confirm provider fee versus customer surcharge; approve Owner authority; amend ADR 0052; create compliance impact declaration if required; confirm local-only rollout. | Index decision gate; finance and architecture review. | Signed decision record and approved API authority. |
| 474.1 Policy API and permission foundation | Add dedicated view/edit capabilities, tenant-scoped route, controller validation, fallback-only use case, repository version transaction, audit, and response DTO. | 474.0; existing tenant revenue module. | Owner can read and create safe fallback version in local fixture; platform fields remain unchanged. |
| 474.2 Transaction and reconciliation hardening | Verify actual versus fallback precedence, snapshot fallback inputs, expose source, correct fallback reconciliation/settlement behavior if needed, and test actual statement correction. | 474.1; finance decision on estimated settlement. | No estimate is presented as actual or settled; reconciliation delta is immutable and idempotent. |
| 474.3 OPIS Owner configuration UX | Add Processing fee policy settings section, method rows, effective-date/reason form, permission states, conflict handling, and responsive accessibility behavior. | 474.1; OPIS manifest and settings editor. | Owner completes local configuration without POS shift or IMS access. |
| 474.4 OPIS payments and reports | Add provider fee summary, source breakdown, transaction columns, policy version, and clear Business amount wording. Reuse canonical tenant revenue reads. | 474.2; existing OPIS payment monitoring and report contracts. | Owner can reconcile displayed totals to API rows and policy snapshot. |
| 474.5 Verification and evidence | Run backend, API, OPIS, security, architecture, documentation, compliance, and local browser checks; capture evidence and update phase ledger only when complete. | 474.1 through 474.4. | All acceptance gates pass; evidence is SHA-bound and local-only. |

# Dependency graph

Governance decision and ADR amendment → permission contract → API validator and use case → repository transaction and snapshot → OPIS settings form → OPIS payment report → tests and local evidence.

Actual provider fee reconciliation is a dependency for finalizing whether fallback-created entries can be settlement-eligible; implementation must not guess.

The first Owner-editable tenant requires a safe platform policy baseline; seed or fixture creation is a rollout dependency, not a silent runtime default.

Phase 473 completion is a ledger eligibility dependency. No new phase number is assigned until the ledger permits Phase 474.

# Parallel work

While the API contract is being reviewed, OPIS wireframes and component-level states can be prepared against fixtures without changing runtime code.

Backend calculation and permission tests can proceed in parallel after the governance decision freezes field names and source semantics.

Report layout and CSV contract tests can be drafted after the response DTO is stable.

# Risks and mitigations

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Financial policy authority conflicts with ADR 0052 read-only tenant rule | Do not implement Owner write until the ADR amendment and finance decision are approved. | Architecture and finance |
| Existing business admin report duplicates tenant revenue logic | Keep tenant revenue module as source of truth; OPIS composes canonical read endpoints. | Backend implementer |
| Fallback estimate changes settlement totals unexpectedly | Keep estimate on hold/exception and reconcile with immutable delta before eligibility. | Finance and backend |
| Shared web-core edit affects IMS | Prefer OPIS-owned UI; if shared code must change, prove all consumers and preserve no IMS feature surface. | Frontend implementer |
| Owner assumes fee is customer charge | Use precise labels and explanatory copy; keep customer surcharge out of this phase. | Product and UX |

# Phase completion conditions

Phase 474 is not completed by code merge alone; all financial, authorization, historical, report, and local evidence gates must pass.

The phase ledger entry must include objective, status completed, dependencies, acceptance evidence, completion date, ADR/API/test links, and implementation file links.

The next eligible phase is Phase 475 only after Phase 474 is recorded completed and the ledger is rechecked.